# Implementation Plan — Day 7 Onwards

A step-by-step build guide for a 4-person team. Each person's tasks are independent: nobody waits on another person's PR to do their own work.

## How this plan stays unblocked

- Backend builds APIs in their own folder.

- Frontend builds pages against committed mock JSON files (under /frontend/mocks/) every day except Day 13, when they swap to the real API. Until then, the UI never depends on the backend being up.

- QA writes test plans, prepares CSV/JSON fixtures, and pre-builds Postman folders — all docs and data, no waiting.

- PM runs the repo: branching rules, code review, README, CHANGELOG, slides, demo plan.

- Each person works on their own feature branch; PM merges to develop. Different folders + different branches = no merge conflicts.

## The Team (4 people)

| Tag | Member / Role | Owns |
| --- | --- | --- |
| P1 | Backend Engineer | Express APIs, PostgreSQL schema, transactions, server config, controllers/models. |
| P2 | Frontend Engineer | All HTML pages, CSS, vanilla JS, Chart.js wiring, Figma-to-page polish, mocks. |
| P3 | QA & Systems Analyst | Postman collection, manual + edge-case testing, bug tickets, user stories, demo data. |
| P4 | Project Manager | Repo admin, branch strategy, code review, merges, README, slides, deployment, docs. |

## Branching strategy at a glance

| Branch | Purpose / Rules |
| --- | --- |
| main | Protected. Only PM merges here. Reflects production-ready releases. |
| develop | Integration branch. All feature branches merge here via PR. Pulled at the start of every day. |
| feature/<scope>-<tag> | Personal task branches, e.g. feature/categories-be, feature/login-orders-ui-fe. One PR each, short-lived. |
| hotfix/<issue-id> | Used Day 17+ for critical bug fixes. Branched from develop, merged the same day. |

### One-time setup (PM, Day 7 morning)

Create develop and protect both branches: $ git checkout main $ git pull origin main $ git checkout -b develop $ git push -u origin develop # GitHub → Settings → Branches → add rule for main and develop: # - Require a pull request before merging # - Require 1 approving review # - Block force pushes

### Daily ritual (everyone, every day)

First thing in the morning, before any work: $ git checkout develop $ git pull origin develop $ git checkout -b feature/<scope>-<tag> # e.g. feature/orders-be # ...do your independent work... $ git add . $ git commit -m "feat(<scope>): short message (#issue)" $ git push -u origin feature/<scope>-<tag> # On GitHub: open a Pull Request — base=develop, compare=your branch # Request review from P4 (PM). PM merges via Squash & Merge.

### If you hit a merge conflict

Pull develop into your branch and resolve: $ git checkout feature/<scope>-<tag> $ git fetch origin $ git merge origin/develop # or: git rebase origin/develop # Open the conflicted files in your editor. Keep the right lines. $ git add <conflicted-files> $ git commit # or: git rebase --continue $ git push # add --force-with-lease if you rebased

### Commit message convention

Use Conventional Commits so the changelog is automatic and reviews are quick:

Examples: feat(orders): add transaction-wrapped POST /api/orders fix(stock): reject decrement when quantity > on-hand (#42) docs(readme): add demo credentials and seed steps test(adjustments): cover damaged-stock validation chore(repo): bump dependencies

## Daily plan — Day 7 to Day 20

Each day below is a clean page. Read your section, run the git ritual, ship your independent piece, open a PR.

# Day 7 — Tuesday, April 29

★ PROPOSAL DEADLINE

Submit Proposal + Categories & Suppliers

Get the proposal submitted in the morning. By end of day, everyone has shipped one independent piece without waiting on anyone else.

### Git ritual for the day

Run these before anything else: $ git checkout develop $ git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · categories + suppliers APIs

Branch: feature/categories-suppliers-be

- Build Categories module: categoryModel.js, categoryController.js, categoryRoutes.js with the 4 standard endpoints + soft delete.

- Build Suppliers module the same way; address split into 5 atomic fields (address_line, barangay, city, province, postal_code).

- Apply authMiddleware to all routes; add roleMiddleware('admin') to POST/PUT/DELETE.

- Every create/update/delete writes an entry to activity_logs via logger.js.

- Open a Pull Request to develop titled 'feat(api): categories + suppliers CRUD' and request P4 as reviewer.

P2 — Frontend Engineer  · static UI from mock JSON

Branch: feature/categories-suppliers-ui-fe

- Create /frontend/mocks/categories.json and /frontend/mocks/suppliers.json with 5 sample rows each. This lets you build UI without waiting for the backend.

- Build categories.html: page layout, header, table, Add/Edit modal, Delete button. Read rows from the mock file.

- Build suppliers.html the same way; modal includes the 5 atomic address fields.

- Match the Figma layout — colors, spacing, font sizes only. No API calls yet.

- Open PR to develop titled 'feat(ui): categories + suppliers static pages'.

P3 — QA & Systems Analyst  · test plan + Postman scaffolding

Branch: feature/qa-categories-suppliers

- Write a one-page test plan for Categories + Suppliers in /docs/tests/categories-suppliers.md. List every endpoint, the success case, and 4 error cases (400, 401, 403, 404).

- In Postman, create the Categories and Suppliers folders with one request per endpoint and the example bodies pre-filled. Save the collection JSON to /postman.

- Create /tests/data/sample_products.csv with 10 valid rows for Day 12's import flow. (Independent prep work — not blocked by anyone.)

- Open PR to develop with the docs and Postman files.

P4 — Project Manager  · submit proposal + repo housekeeping

Branch: feature/proposal-submission-pm

- Final formatting pass on the proposal: page numbers, table of contents, cover page filled in.

- Export the proposal as PDF (keep the .docx as a backup) and submit before the deadline.

- Update README with a 'Branching Strategy' section that mirrors the cheat sheet on page 3 of this document.

- Review every PR opened today and merge them in any order — they touch different folders so conflicts are impossible.

- End of day: tag develop with phase1-end (git tag -a phase1-end -m "Phase 1 complete" && git push --tags).

### Done when

- Proposal is submitted on time.

- Each person has a merged PR. Nobody was blocked.

- Postman collection now contains Categories and Suppliers folders.

# Day 8 — Wednesday, April 30

Locations & Stock Logic

Build the Locations module and the helper functions that keep stock numbers correct. Frontend keeps using mock data so it stays unblocked.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · locations + stock helpers

Branch: feature/locations-stock-be

- Build the Locations module (model + controller + routes) — 4 endpoints with soft delete; address split into atomic fields.

- Create /backend/src/models/stockModel.js with: getStockByProduct(productId), getStockByLocation(locationId), incrementStock(productId, locationId, qty, dbClient), decrementStock(...). Use row-level locks inside transactions.

- Wire up GET /api/products/:id/stock from Day 6 to call getStockByProduct.

- Open PR titled 'feat(api): locations + stock helpers'.

P2 — Frontend Engineer  · global CSS + locations UI

Branch: feature/global-css-locations-fe

- Write the global CSS — style.css and sidebar.css. Define color tokens, spacing, font sizes that match Figma.

- Build a static dashboard.html mockup with all the cards laid out (no charts yet).

- Build locations.html with a mock /frontend/mocks/locations.json file. Table + Add/Edit modal with the atomic address fields.

- Open PR titled 'feat(ui): global css + locations static page'.

P3 — QA & Systems Analyst  · stock-logic test plan

Branch: feature/qa-locations-stock

- Write a stock-helper test plan: success case for incrementStock, success for decrementStock, failure when decrementing below zero, idempotency on retry.

- Add Locations folder to Postman with all 4 endpoints + auth header pre-set.

- Draft /docs/tests/concurrency.md outlining how to test two simultaneous stock-out requests on Day 17.

- Open PR with the docs + updated Postman JSON.

P4 — Project Manager  · branch protection + standups

Branch: feature/branch-protection-pm

- Enable branch protection on main and develop in GitHub Settings: require PR + 1 approval, block force pushes, require status checks if you have CI.

- Write /docs/standup-template.md (date, what each person did, what they'll do, blockers).

- Run today's 15-minute stand-up; capture notes.

- Review and merge today's PRs in any order — different folders, no conflicts.

### Done when

- Locations CRUD works in Postman against the live backend.

- Stock helper functions can increment and decrement correctly.

- Frontend Locations page renders cleanly using mock data.

- All four PRs merged with zero merge conflicts.

# Day 9 — Thursday, May 1

Stock-In and Stock-Out (Orders)

Build the orders module — the heart of the inventory system. Frontend builds the login page and the orders list using mocks.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · orders module with transactions

Branch: feature/orders-be

- Build the Orders module (model + controller + routes).

- POST /api/orders inside a database transaction: insert orders → for each item insert order_items + incrementStock (IN), decrementStock (OUT), or both (TRANSFER) → upsert product_batches if the IN order has batch info → write activity_logs → COMMIT or ROLLBACK on any error.

- GET /api/orders with filters: ?order_type, ?location_id, ?date_from, ?date_to.

- PUT /api/orders/:id allows updating notes and reference_no only — never quantities.

- DELETE /api/orders/:id soft-deletes AND reverses the stock changes.

P2 — Frontend Engineer  · login page + orders UI from mocks

Branch: feature/login-orders-ui-fe

- Build login.html with a working form. Wire it to a small mock auth helper that accepts admin/admin123 and stores a fake token in sessionStorage. (Real backend will be plugged in on Day 13.)

- Add a route guard snippet to dashboard.html that redirects to login.html if no token.

- Build orders.html as a list page using /frontend/mocks/orders.json. Add date-range and type filters that filter the in-memory array.

- Open PR titled 'feat(ui): login + orders static pages'.

P3 — QA & Systems Analyst  · orders test plan

Branch: feature/qa-orders

- Write the Orders test plan: stock-in (verify product_stock.quantity increased), stock-out (decreased), stock-out with insufficient stock (400), TRANSFER between locations.

- Document the concurrency test (two browser windows / two Postman tabs hitting POST simultaneously).

- Add the Orders folder to Postman with one example per scenario.

P4 — Project Manager  · release notes + issue triage

Branch: feature/changelog-pm

- Create CHANGELOG.md and start a 'Phase 2' section. Add one bullet per merged PR.

- Sweep open issues; add labels (backend, frontend, qa, docs); assign owners.

- Review and merge today's four PRs.

### Done when

- Stock-in adds to product_stock correctly; stock-out subtracts and rejects if insufficient.

- Login page works in the browser with the mock auth helper.

- Orders list page renders from mock data with working filters.

# Day 10 — Friday, May 2

Stock Adjustments & Reason Codes

Build the manual stock-correction module. Frontend builds the dashboard shell. QA documents the reason-code rules.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · adjustments + reason codes

Branch: feature/adjustments-be

- Build the Reason Codes module — GET (list all) and POST (admin only).

- Build the Stock Adjustments module — 4 endpoints with soft delete.

- POST validation: reason_code_id is required, must exist, must not be soft-deleted, and the adjustment_type must match what the reason code allows (e.g., DAMAGED is decrease only).

- Wrap each adjustment in a transaction: insert into stock_adjustments AND update product_stock.quantity in the same transaction.

- Build GET /api/products/:id/history — query the stock_movements view JOINed with users, locations, batches, reason_codes.

P2 — Frontend Engineer  · dashboard shell + sidebar

Branch: feature/dashboard-shell-fe

- Build dashboard.html shell: sidebar, header, empty card placeholders. No data needed.

- Build sidebar.js: highlight the active link based on the current URL.

- Make every existing static page include the same sidebar/header components.

- Wire login → dashboard navigation end-to-end (still using mock auth).

P3 — QA & Systems Analyst  · adjustments test matrix

Branch: feature/qa-adjustments

- Write a reason-code matrix in /docs/tests/reason-codes.md: 8 default codes × allowed adjustment_type. This becomes the spec the BE validation must match.

- List edge cases: missing reason_code, soft-deleted reason code, mismatched adjustment_type.

- Add Adjustments + Reason Codes folders to Postman with one test per edge case.

P4 — Project Manager  · polish list + Figma walkthrough

Branch: feature/polish-list-pm

- Run a 20-minute Figma walkthrough: compare current UI to Figma side by side. Note every delta in /docs/polish.md (will be used on Day 18).

- Update CHANGELOG and post a daily summary in the group chat.

- Review and merge today's PRs.

### Done when

- All 4 adjustment endpoints work and validate correctly.

- Stock movement history endpoint returns chronological list.

- Dashboard shell shows in browser; sidebar links navigate between pages.

# Day 11 — Saturday, May 3

Batches & Expiry Tracking

Track expiry dates per batch. Frontend builds the shared API helper and utils so Day 13 can plug in real data fast.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · batches + expiry index

Branch: feature/batches-be

- Build the Batches module — 4 CRUD endpoints + soft delete.

- Add GET /api/batches/expiring?days=30 — returns batches where expiry_date is within N days from today.

- Validation: only allow batch creation if the product has track_expiry = TRUE.

- Update the Day 9 orders code so an IN order with batch info auto-creates or updates the batch.

- Add a DB index: CREATE INDEX idx_batches_expiry ON product_batches(expiry_date) WHERE is_deleted = FALSE.

P2 — Frontend Engineer  · api.js + utils.js

Branch: feature/api-utils-fe

- Build /frontend/js/api.js — a wrapper around fetch() that auto-attaches the JWT from sessionStorage and handles errors centrally. Make BASE_URL configurable so it can also read mocks during dev.

- Build /frontend/js/utils.js — date formatter, toast notifier, currency formatter (₱).

- Stub batches.html with mock data showing color-coded expiry rows. (Wiring to real API happens Day 15.)

P3 — QA & Systems Analyst  · batches test plan

Branch: feature/qa-batches

- Write the Batches test plan covering all 5 endpoints.

- Prepare /tests/data/batches-expiry.json — sample batch rows with mixed expiry windows for Day 17 regression testing.

- Add Batches folder to Postman with one example for each test case.

P4 — Project Manager  · README + onboarding

Branch: feature/readme-pm

- Write the first full README: project overview, tech stack, prerequisites, setup steps (clone, npm install, create db, run schema/views/seeds, start server), demo credentials.

- Add a 'How to import the Postman collection' section.

- Review and merge today's four PRs.

### Done when

- All 5 batch endpoints work; /api/batches/expiring?days=30 returns correctly.

- api.js and utils.js are committed and used by at least one existing page.

- README is good enough that a new teammate could clone and run it.

# Day 12 — Sunday, May 4

Import / Export & Reports

Bulk CSV/Excel and report endpoints. After today the backend is feature-complete.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · import/export + reports

Branch: feature/import-export-reports-be

- Build /backend/src/middleware/uploadMiddleware.js using Multer (.csv and .xlsx only, max 5MB).

- Build csvHelper.js (papaparse) and excelHelper.js (exceljs) — each with parse and serialize functions.

- Build POST /api/import/products: parse → validate every row → all-or-nothing insert in a transaction. If any row fails, return an error report and write nothing.

- Build GET /api/export/products?format=csv|xlsx, plus /api/export/stock-report and /api/export/movement-log.

- Build the Reports endpoints: /api/reports/dashboard, /low-stock, /expiring, /stock-summary, /movement-log.

P2 — Frontend Engineer  · dashboard wiring (mock-first)

Branch: feature/dashboard-mock-fe

- Create /frontend/mocks/dashboard.json with the same shape /api/reports/dashboard will return.

- Build dashboard.js: render summary cards from the mock file.

- Add Chart.js via CDN; render the Stock-by-Location bar chart using mock data.

- Add the logout button to the header — clears sessionStorage and redirects to login.

P3 — QA & Systems Analyst  · CSV test files + import flow

Branch: feature/qa-import

- Prepare three CSV test files: products_valid.csv (10 valid rows), products_missing_fields.csv, products_duplicate_skus.csv. Save to /tests/data/.

- Write /docs/tests/import.md describing the expected response for each file.

- By end of day, Postman should document all 47 endpoints — export the collection JSON.

P4 — Project Manager  · tag backend-complete

Branch: feature/release-notes-phase2-pm

- Tag end-of-day: git tag -a backend-complete -m "Backend feature-complete" && git push --tags.

- Draft Phase 2 release notes in CHANGELOG.md.

- Confirm dashboard cards show numbers from the mock file in the browser.

### Done when

- Backend has all 47 endpoints working.

- Bad CSV import returns a clear error and changes nothing in the database.

- Dashboard cards show numbers from the mock data.

# Day 13 — Monday, May 5

Frontend Foundation — Switch to Real Backend

Today is the only day the frontend depends on the backend being up. Plan accordingly: P1 keeps the server running, P2 swaps mocks for real APIs.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · performance + error shape

Branch: feature/api-perf-be

- Profile slow endpoints; add basic indexes where needed.

- Standardize error responses across every endpoint to { error, message, fields? }.

- Add pagination to /api/products and /api/orders (?page, ?limit).

- Stay on call to answer FE questions when they swap from mocks to real APIs.

P2 — Frontend Engineer  · live dashboard end-to-end

Branch: feature/dashboard-live-fe

- In api.js, switch BASE_URL from 'mocks/' to 'http://localhost:5000/api'.

- Replace dashboard.js mock fetches with real /api/reports/dashboard call.

- Finalize all CSS files (style.css, sidebar.css, dashboard.css, tables.css, forms.css, alerts.css).

- Wire login.html to call POST /api/auth/login for real (replace the mock auth helper).

- Add the route-protection snippet to every HTML page.

P3 — QA & Systems Analyst  · auth flow regression

Branch: feature/qa-auth-regression

- Test the full login → dashboard → logout flow on Chrome and Firefox; capture screenshots.

- Verify expired/missing token redirects to login.

- File any regressions as GitHub Issues with steps + expected vs actual.

P4 — Project Manager  · polish backlog + RC plan

Branch: feature/polish-backlog-pm

- Convert /docs/polish.md into individual GitHub Issues, labelled 'polish'.

- Schedule them against the Day 18 milestone.

- Review and merge PRs; verify dashboard renders live numbers in the browser.

### Done when

- Login → Dashboard → Logout works against the real backend.

- Dashboard shows real numbers and the bar chart renders.

- Visiting any page without a token redirects to login.

# Day 14 — Tuesday, May 6

Products / Categories / Suppliers UI

Convert three CRUD pages from mock-driven to API-driven.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · validation hardening

Branch: feature/validation-be

- Tighten request validation on Products / Categories / Suppliers — mirror the FE rules on the server.

- Return field-level errors in a consistent shape: { error: 'ValidationError', fields: [...] }.

- Add numeric guards on price and quantity (no negatives, sane upper bounds).

P2 — Frontend Engineer  · wire 3 CRUD pages live

Branch: feature/products-categories-suppliers-fe

- Wire products.html / categories.html / suppliers.html to the real APIs through api.js.

- Add a search bar and dropdown filters above the products table.

- Add client-side validation on the product form (required fields, SKU format, numeric price/qty).

- Add a global toast (green for success, red for error) and a confirmation dialog for every delete.

P3 — QA & Systems Analyst  · smoke pass + bug filing

Branch: feature/qa-day14

- Smoke-test every page; file any bugs as GitHub Issues with steps, expected behavior, actual behavior, and a screenshot.

- Cover validation paths: required fields, SKU format, numeric checks.

- Run all Postman tests for the three modules end-to-end.

P4 — Project Manager  · issue triage

Branch: feature/triage-pm

- Triage today's issues into Critical / High / Medium / Low.

- Reassign each to the right owner and add to milestone 'Day 17 Bug Fix'.

- Update CHANGELOG; merge today's PRs.

### Done when

- Products / Categories / Suppliers pages support full CRUD via the UI.

- Validation errors are shown clearly to the user.

- Delete actions ask for confirmation.

# Day 15 — Wednesday, May 7

Locations / Batches / Orders / Adjustments UI

Build four more pages, including the dynamic-row order form.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · patch + reason-code endpoint

Branch: feature/api-patches-be

- Patch any endpoints surfaced by FE work (extra fields, dropdown options, ordering).

- Add /api/reason-codes/:id/allowed-types — returns the adjustment_types each reason code permits (drives the FE adjustment form).

- Confirm the TRANSFER endpoint returns both updated stock rows in its response.

P2 — Frontend Engineer  · 4 live CRUD pages

Branch: feature/four-pages-fe

- Wire locations.html live (table + Add/Edit modal with atomic address fields).

- Wire batches.html live with color-coded expiry: green ≥90d, yellow 30–90d, red <30d, dark red expired.

- Wire orders.html live with date-range, type, and location filters.

- Build the New Order form with dynamic 'Add Item' rows; fields change with order_type (IN: Destination + Supplier; OUT: Source; TRANSFER: Source + Destination).

- Wire adjustments.html — list view + New Adjustment form. The available adjustment_type depends on the selected reason code (call /allowed-types).

- Add the Stock-by-Category pie chart and dashboard auto-refresh every 60s when the tab is visible.

P3 — QA & Systems Analyst  · dynamic form testing

Branch: feature/qa-dynamic-form

- Walk the dynamic order form through every type combination and verify the resulting stock movements.

- Verify the adjustments form enforces the reason-code rules from your Day 10 matrix.

- File any new bugs against the right owner.

P4 — Project Manager  · mid-week status

Branch: feature/status-day15-pm

- Run a 15-minute mid-week status update; capture risks and blockers.

- Document remaining Figma deltas in /docs/polish.md.

- Review and merge PRs; tag develop end of day.

### Done when

- All 4 pages support full CRUD via the UI.

- Batch list shows color-coded expiry indicators.

- Both dashboard charts render correctly.

# Day 16 — Thursday, May 8

History / Reports / Import-Export / Users / Profile UI

Build the last 5 pages. After today the system is functional end-to-end.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · admin guards + password change

Branch: feature/admin-password-be

- Confirm /api/users routes are admin-locked end-to-end (middleware + DB queries).

- Add a self-service endpoint POST /api/users/me/password — verifies old password before updating.

- Make the import response richer: { ok, total, inserted, errors: [{ row, message }] }.

P2 — Frontend Engineer  · 5 final pages

Branch: feature/final-pages-fe

- stock-history.html — opens via a 'View History' link on each product. Full timeline with date, type, quantity, location, who, reason.

- reports.html — tabs for Low Stock, Expiring Soon, Stock Summary, Movement Log; each tab has an Export button that calls /api/export/...

- import-export.html — drag-and-drop upload area for CSV/Excel; shows a per-row success/error report after upload.

- users.html — table with role badges + Add/Edit modal. Hide the Users menu item for staff users.

- profile.html — current user info + change-password form.

P3 — QA & Systems Analyst  · begin E2E pass

Branch: feature/qa-e2e-day16

- Begin a systematic end-to-end test pass: every page, every action, both Admin and Staff roles.

- Confirm staff users cannot see the Users menu and are blocked at the API layer too.

- Validate the import flow against valid + invalid CSV files prepared on Day 12.

P4 — Project Manager  · cut release candidate

Branch: feature/rc1-pm

- Cut RC1 tag: git tag -a v1.0-rc1 -m "RC1 — feature-complete" && git push --tags.

- Lock develop to PRs only (require review).

- Update README screenshots.

### Done when

- All 16 pages are built and accessible.

- Import flow handles valid and invalid files cleanly.

- Staff users cannot see the Users menu.

# Day 17 — Friday, May 9

Test Everything & Fix Bugs

No new features today. Find bugs, then fix the bugs assigned to you. Each person works on their own queue — fully independent.

### Git ritual for the day

Run these before anything else: Bug fixes branch from develop using a hotfix prefix: $ git checkout develop && git pull origin develop $ git checkout -b hotfix/<short-issue-id> After PR is merged, delete the branch: $ git push origin --delete hotfix/<short-issue-id>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · fix BE bugs

Branch: hotfix/be-<issue-id>

- Pull your queue: every issue labelled 'backend' assigned to you.

- One branch per fix. Open one PR per fix titled 'fix(scope): summary (#issue)'.

- Re-run the relevant Postman tests after each fix.

P2 — Frontend Engineer  · fix FE bugs

Branch: hotfix/fe-<issue-id>

- Pull your queue: every issue labelled 'frontend' assigned to you.

- Re-test on a fresh sessionStorage to catch token edge cases.

- Each fix is its own branch and PR — keeps reviews tight.

P3 — QA & Systems Analyst  · lead the test pass

Branch: feature/qa-test-pass

- Run the full test list (every CRUD on every entity, both Admin and Staff).

- Run the high-risk scenarios: concurrent stock-out in two windows, bad CSV import, negative stock attempt, expired session, soft-deleted product visibility, soft-delete a category that has products.

- File each bug as a GitHub Issue with steps, expected, actual, and a screenshot if visual.

P4 — Project Manager  · triage + Postman + report

Branch: feature/postman-final-pm

- Triage every new bug into Critical / High / Medium / Low; assign owners.

- Goal: zero Critical bugs open by EOD.

- Finalize the Postman collection — every endpoint has an example with auth header. Export to /postman/collection.json.

- Save the test report to /docs/test-report.md.

### Done when

- All Critical and High bugs resolved.

- Postman collection exported and committed.

- Test report saved to /docs.

# Day 18 — Saturday, May 10

Polish & Demo Data

Make the system look professional and load impressive demo data.

### Git ritual for the day

Run these before anything else: $ git checkout develop && git pull origin develop $ git checkout -b feature/<your-scope>-<your-tag>

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · demo data SQL

Branch: feature/demo-data-be

- Write /database/demo_data.sql with: 3 locations (Main Warehouse, Branch Store, Cold Storage), 5 categories, 5 suppliers, 20 products mixing track_expiry and varied stock.

- At least 3 products below their reorder_level (so the low-stock alert lights up).

- 5+ batches with expiry dates inside the next 30 days.

- 30+ historical orders and 10+ adjustments to populate the dashboard.

- Reload a clean DB end-to-end: schema → views → reason_codes_seed → demo_data. Verify it runs in one go.

P2 — Frontend Engineer  · polish list

Branch: feature/polish-fe

- Walk the polish list from Day 13 — fix spacing, alignment, hover and focus states.

- Test on 1366×768 and 1920×1080. Fix any layout breaks.

- Empty states for every list (e.g., 'No products yet — add your first one').

- Loading indicators (spinner or skeleton) for slow API calls.

- Error states with a retry button on network failure.

P3 — QA & Systems Analyst  · polish regression

Branch: feature/qa-polish

- Re-test every page after polish; confirm no regressions.

- Verify the dashboard looks lively with demo data (numbers, charts, alerts).

- Continue knocking down Medium/Low bugs from your queue.

P4 — Project Manager  · RC2 + screenshots

Branch: feature/rc2-pm

- Tag end-of-day as v1.0-rc2: git tag -a v1.0-rc2 -m "RC2 — polish + demo data" && git push --tags.

- Update README screenshots and the Setup section to reference demo_data.sql.

- Confirm a fresh clone install works on the demo laptop.

### Done when

- UI is polished — no obvious layout problems.

- Empty / loading / error states are handled.

- Demo dataset loads cleanly and produces a great-looking dashboard.

# Day 19 — Sunday, May 11

Final Test & Defense Practice

Lock the code. Practice the demo. Each person preps their own slot.

### Git ritual for the day

Run these before anything else: PM merges develop → main and tags v1.0-defense: $ git checkout main && git pull origin main $ git merge --no-ff develop -m "Merge develop for v1.0-defense" $ git tag -a v1.0-defense -m "Defense build" && git push --tags After this, only hotfix branches off main are allowed.

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · Postman demo prep

Branch: hotfix/critical-only

- Pre-organize the Postman collection in the order you will demo. Set environment variables.

- Be ready to answer database / API questions (transactions, soft delete, indexes, the stock_movements view).

- Only critical fixes today. Open a hotfix branch, merge fast, move on.

P2 — Frontend Engineer  · presentation laptop check

Branch: hotfix/critical-only

- Test the full system on the actual presentation laptop (not your dev machine).

- Confirm demo data renders charts and alerts properly.

- Verify zoom 110–125% looks clean. Check projector resolution.

P3 — QA & Systems Analyst  · test report + user stories

Branch: feature/test-summary-qa

- Prepare a test report summary: X test cases run, Y passed, Z bugs fixed.

- Bring the user-stories doc and align them with implemented features.

- Stage one panelist as a 'tough questioner' during the dry-run.

P4 — Project Manager  · lead dry-run + slides

Branch: main (merge)

- Lock main on GitHub (require PR + review).

- Lead a full demo dry-run with the team using the Demo Flow script.

- Prepare 5–10 slides: title, problem, solution, tech stack, key features, demo, Postman, conclusion, future work, thank you.

- Write the contingency plan: Wi-Fi → mobile hotspot, laptop → backup laptop, missing artifact → printed proposal.

- Final commit + tag v1.0-defense; push tags.

### Done when

- Full demo dry-run completed successfully.

- Slides ready and reviewed.

- Contingency plan documented.

# Day 20 — Monday, May 12

★ FINAL DEFENSE — Show Off Your Work

Deliver the demo cleanly. No code changes today.

### Git ritual for the day

Run these before anything else: No commits to main on defense day. If a critical fix is unavoidable: $ git checkout -b hotfix/defense-<short> Verify, get panel approval if appropriate, fast-forward merge, tag v1.0-defense+1.

### Tasks per person (independent — no one is blocked)

P1 — Backend Engineer  · DB design + Postman demo

Branch: —

- Walk the database design: 12 tables, the stock_movements view, 3NF (1–2 min).

- Postman demo of 4–5 key endpoints (3 min).

- Field DB / API panel questions.

P2 — Frontend Engineer  · live demo

Branch: —

- Lead the live system demo per the Demo Flow (5–7 min).

- Field UI / UX questions; show responsive behavior if asked.

P3 — QA & Systems Analyst  · problem + scope + quality

Branch: —

- Present the problem, scope, and user stories (2 min).

- Be ready with test report numbers when quality comes up.

P4 — Project Manager  · open + close + Q&A

Branch: —

- Open with introductions and project overview (2–3 min).

- Closing — summarize features, acknowledge limitations, thank panel (1 min).

- Coordinate Q&A: route each question to the right owner.

- Capture panel feedback in /docs/post-defense.md.

### Done when

- Demo delivered cleanly.

- All panel questions addressed.

- Post-defense feedback captured.